## Budget
|  | TEAMS | Days to complete per Gantt | Labor Hours | BAC | %Complete on day 12 |  | AC Hours | $AC
MGT2_KKM1: Monitoring and Controlling Task 3 project Joette Damo |  | Team Phase 1 Premigration - Sara Patel | 8 | 112 | 8400 |  | 100% | 122 | 9150
Information - Synesthor Cloud Storage Migration Project |  | Team Phase 2 Storage - Sophia Miller | 18 | 144 | 10800 |  | 58% | 99 | 7425
Start date July 1 owners want project done by December 1
Labor costs expectation: | 124800 | Team Phase 3 Off-site cloud system - Daniel Johnson | 43 | 552 | 41400 |  | 3% | 16 | 1200
Standard overhead labor rate : | 75
Budgeted hours: | 1,664 hours | Team Phase 4 Testing - Talia Phan | 78 | 712 | 53400 |  | 5% | 32 | 2400
Hours in a work day: | 8 | Team Phase 5 Migration - Omar Thomas | 18 | 144 | 10800 |  | 0% | 0 | 0
|  | Totals | 165 | 1664 | 124800 |  |  | 269 | 20175

## C1 Earned Value Analysis
TEAMS | Days to complete per Gantt | Labor Hours | BAC | %Complete on day 12 |  | AC Hours | $AC | EV | Planned% | PV | CV | CPI | SV | SPI
Team Phase 1 Premigration - Sara Patel | 8 | 112 | 8400 |  | 100% | 122 | 9150 | 8400 | 100% | 8400 | -750 | 0.91803 | 0 | 1
Team Phase 2 Storage - Sophia Miller | 18 | 144 | 10800 |  | 58% | 99 | 7425 | 6264 | 66.67% | 7200 | -1161 | 0.84364 | -936 | 0.87
Team Phase 3 Off-site cloud system - Daniel Johnson | 43 | 552 | 41400 |  | 3% | 16 | 1200 | 1242 | 3.125% | 1293.75 | 42 | 1.035 | -51.75 | 0.96
Team Phase 4 Testing - Talia Phan (Critical Path in Gantt Chart) | 78 | 712 | 53400 |  | 5% | 32 | 2400 | 2670 | 2.564% | 1369.2308 | 270 | 1.1125 | 1300.7692 | 1.95
Team Phase 5 Migration - Omar Thomas | 18 | 144 | 10800 |  | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
Totals | 165 | 1664 | 124800 |  | 33.2% | 269 | 20175 | 18576 | 34.47% | 18262.9808 | -1599 | 0.78183 | 313.0192 | 0.956
EV = Earned Value = % Complete * BAC
Planned% = days completed based upon calendar/Gantt chart totals days for phase
PV = Planned Variance = Planned%*BAC
CV = Cost Variance = EV - AC
CPI = Cost Performance Index = EV/AC
SV = Schedule Variance = EV - PV
SPI = Schedule Performance Index = EV/PV

## C2 Earned Value Projections
TEAMS | Days to complete per Gantt | Labor Hours | BAC | %Complete on day 12 |  | AC Hours | $AC | EV | Planned% | PV | CV | CPI | SV | SPI | EAC | ETC | Original durations | Estimated Duration | Est Complete date | PCIB
Team Phase 1 Premigration - Sara Patel | 8 | 112 | 8400 |  | 100% | 122 | 9150 | 8400 | 100% | 8400 | -750 | 0.91803 | 0 | 1 | 9130.4348 | -19.5652 | 8 | 8 | 2021-07-14 | 100%
Team Phase 2 Storage - Sophia Miller | 18 | 144 | 10800 |  | 58% | 99 | 7425 | 6264 | 66.67% | 7200 | -1161 | 0.84364 | -936 | 0.87 | 12857.1429 | 5432.1429 | 18 | 20.6897 | 2021-07-28 | 58%
Team Phase 3 Off-site cloud system - Daniel Johnson | 43 | 552 | 41400 |  | 3% | 16 | 1200 | 1242 | 3.125% | 1293.75 | 42 | 1.035 | -51.75 | 0.96 | 39807.6923 | 38607.6923 | 64 | 66.6667 | 2021-09-15 | 3%
Team Phase 4 Testing - Talia Phan (Critical Path in Gantt Chart) | 78 | 712 | 53400 |  | 5% | 32 | 2400 | 2670 | 2.564% | 1369.2308 | 270 | 1.1125 | 1300.7692 | 1.95 | 48108.1081 | 45708.1081 | 78 | 40 | 2021-11-03 | 5%
Team Phase 5 Migration - Omar Thomas | 18 | 144 | 10800 |  | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 2021-10-11 | 0%
Totals | 165 | 1664 | 124800 |  | 33.2% | 269 | 20175 | 18576 | 34.47% | 18262.9808 | -1599 | 0.78183 | 313.0192 | 0.956 | 109903.3781 | 89728.3781
[15 empty] | Variance | 14896.6219
EV = Earned Value = % Complete * BAC
Planned% = days completed based upon calendar/Gantt chart totals days for phase
PV = Planned Variance = Planned%*BAC
CV = Cost Variance = EV - AC
CPI = Cost Performance Index = EV/AC
SV = Schedule Variance = EV - PV
SPI = Schedule Performance Index = EV/PV
EAC = Estimate at completion = EAC = BAC/CPI
ETC = Estimate to complete = ETC = EAC - AC
Estimate Duration = Planned Duration/SPI (From Gantt Chart)
PCIB = Percent Complete Index Budget = PCIB = EV/BAC
TCPI = To Complete Performance Index = TCPI = (BAC-EV)(BAC-AC)
Estimate Duration = duration of job/SPI (From Gantt Chart)
EAC – Estimate at completion EAC = BAC/CPI (Use this if CPI is expected to be the same for the remainder of the project)
This amount is currently expected to be spent by the end of the project which is an estimate.
ETC – Estimate to complete (ETC = EAC – AC)
This amount will determine how much will likely be spent to finish the project.
Estimated Duration in days
These are the estimate number of days left to complete the project.
Estimated completion date
These are estimated dates to complete the project based upon the Gantt Chart and calendar year of 2021.

## D1 Burndown Chart
Days | Ideal Burndown | Actual Burndown
5 | 25 | 25 | July
6 | 24.7093 | 24
7 | 24.4186 | 24
8 | 24.1279 | 21
9 | 23.8372 | 21
12 | 23.5465 | 20
13 | 23.2558 | 20
14 | 22.9651 | 18
15 | 22.6744 | 18
16 | 22.3837 | 17
19 | 22.093 | 17
20 | 21.8023 | 17
21 | 21.5116
22 | 21.2209
23 | 20.9302
26 | 20.6395
27 | 20.3488
28 | 20.0581
29 | 19.7674
30 | 19.4767
2 | 19.186 |  | August
3 | 18.8953
4 | 18.6047
5 | 18.314
6 | 18.0233
9 | 17.7326
10 | 17.4419
11 | 17.1512
12 | 16.8605
13 | 16.5698
16 | 16.2791
17 | 15.9884
18 | 15.6977
19 | 15.407
20 | 15.1163
23 | 14.8256
24 | 14.5349
25 | 14.2442
26 | 13.9535
27 | 13.6628
30 | 13.3721
31 | 13.0814
1 | 12.7907 |  | Sept
2 | 12.5
3 | 12.2093
6 | 11.9186
7 | 11.6279
8 | 11.3372
9 | 11.0465
10 | 10.7558
13 | 10.4651
14 | 10.1744
15 | 9.8837
16 | 9.593
17 | 9.3023
20 | 9.0116
21 | 8.7209
22 | 8.4302
23 | 8.1395
24 | 7.8488
27 | 7.5581
28 | 7.2674
29 | 6.9767
30 | 6.686
1 | 6.3953 |  | Oct
4 | 6.1047
5 | 5.814
6 | 5.5233
7 | 5.2326
8 | 4.9419
11 | 4.6512
12 | 4.3605
13 | 4.0698
14 | 3.7791
15 | 3.4884
18 | 3.1977
19 | 2.907
20 | 2.6163
21 | 2.3256
22 | 2.0349
25 | 1.7442
26 | 1.4535
27 | 1.1628
28 | 0.87209
29 | 0.5814
1 | 0.2907 |  | Nov