## Sheet1
Table 7-1. Earned Value Calculations Summary Table
Taken from the Project Management Body of Knowledge, 6th edition
Earned Value Analysis
Abbreviation | Name | Lexicon Definition | How Used | Equation | Interpretation of Result
PV | Planned Value | The authorized budget assigned to scheduled work. | The value of the work planned to be completed to a point in time, usually the data date, or project completion. | PV = Planned % Complete X Budget at Completion
EV | Earned Value | The measure of work performed expressed in terms of the budget authorized for that work. | The planned value of all the work completed (earned) to a point in time, usually the data date, without reference to actual costs. | EV = % Complete as of Today X Budget at Completion
AC | Actual Cost | The realized cost incurred for the work performed on an activity during a specific time period. | The actual cost of all the work completed to a point in time, usually the data date.
BAC | Budget at Completion | The sum of all budgets established for the work to be performed. | The value of total planned work, the project cost baseline.
CV | Cost Variance | The amount of budget deficit or surplus at a given point in time, expressed as the difference between the earned value and the actual cost. | The difference between the value of work completed to a point in time, usually the data date, and the actual costs to the same point in time. | CV = EV − AC | Positive − Under planned cost
Neutral − On planned cost
Negative − Over planned cost
SV | Schedule Variance | The amount by which the project is ahead or behind the planned delivery date, at a given point in time, expressed as the difference between the earned value and the planned value. | The difference between the work completed to a point in time, usually the data date, and the work planned to be completed to the same point in time. | SV = EV − PV | Positive − Ahead of Schedule
Neutral − On schedule
Negative − Behind Schedule
VAC | Variance at Completion | A projection of the amount of budget deficit or surplus, expressed as the difference between the budget at completion and the estimate at completion. | The estimated difference in cost at the completion of the project. | VAC = BAC − EAC | Positive − Under planned cost
Neutral − On planned cost
Negative − Over planned cost
CPI | Cost Performance Index | A measure of the cost efficiency of budgeted resources expressed as the ratio of earned value to actual cost. | A CPI of 1.0 means the project is exactly on budget, that the work actually done so far is exactly the same as the cost so far. Other values show the percentage of how much costs are over or under the budgeted amount for work accomplished. | CPI = EV/AC | Greater than 1.0 − Under planned cost
Exactly 1.0 − On planned cost
Less than 1.0 − Over planned cost
SPI | Schedule Performance Index | A measure of schedule efficiency expressed as the ratio of earned value to planned value. | An SPI of 1.0 means that the project is exactly on schedule, that the work actually done so far is exactly the same as the work planned to be done so far. Other values show the percentage of how much costs are over or under the budgeted amount for work planned. | SPI = EV/PV | Greater than 1.0 − Ahead of schedule
Exactly 1.0 − On schedule
Less than 1.0 − Behind schedule
EAC | Estimate At Completion | The expected total cost of completing all work expressed as the sum of the actual cost to date and the estimate to complete. | If the CPI is expected to be the same for the remainder of the project, EAC can be calculated using: | EAC = BAC/CPI | Amount currently expected to be spent by the end of the project - just an estimate, so don't read too much into it.
|  |  | If future work will be accomplished at the planned rate, use: | EAC = AC + BAC − EV
|  |  | If the initial plan is no longer valid, use: | EAC = AC + Bottom-up ETC
|  |  | If both the CPI and SPI influence the remaining work, use: | EAC = AC + [(BAC − EV)/(CPI x SPI)]
ETC | Estimate to Complete | The expected cost to finish all the remaining project work. | Assuming work is proceeding on plan, the cost of completing the remaining authorized work can be calculated using: | ETC = EAC − AC | How much will likely be spent to finish the project.
|  |  | Reestimate the remaining work from the bottom up. | ETC = Reestimate
TCPI | To Complete Performance Index | A measure of the cost performance that must be achieved with the remaining resources in order to meet a specified management goal, expressed as the ratio of the cost to finish the outstanding work to the budget available. | The efficiency that must be maintained in order to complete within the originally planned budget. | TCPI = (BAC − EV)/(BAC − AC) | Greater than 1.0 − Harder to complete, must be more efficient
|  |  | The efficiency that must be maintained in order to complete using a baseline using one of the EAC formulas, different than the original budget. | TCPI = (BAC − EV)/(EAC − AC) | Exactly 1.0 − The work done so far is on budget, so the work left to complete can keep going at the same rate
Less than 1.0 − The work done so far has been under budget, so the rest of the work can be less efficient and still come out on budget
Taken from Project Management. 12th edition by Harold Kerzner, PhD.
Estimated Duration |  | How long the project will take to complete based on the current performance calculated using the SPI | Using the SPI, you can calculate the new completion date for the project by dividing the Planned Duration by the resulting SPI for project. Take the new number of days and count out on the calendar the new date they will finish. | Estimated Duration = Planned Duration/SPI | How many days will that piece of the project take? Compare to the original budget to determine how many days early or late it will be.
Taken from Project Management, Acrobatiq
PCIC | Percent Complete Index-Cost | Measurement of how much total project work has been completed using AC, compared to the new budget (EAC) which will replace the baseline budget (BAC). | Used after the new budget has been agreed upon. Actual costs are compared to new budget in a ratio to determine percent of work completed compared to EAC (revised budget). | PCIC=AC/EAC | Once you have a value for AC/EAC, you will know what percent of work should have been completed by the day selected.
PCIB | Percent Complete Index-Budget | Measurement of how much of the total project work has been completed based on the original baseline budget. | Can be used to calculate the amount of work completed at any given time during the project, if the original budget is still appropriate to use for the project. This is just the EV formula flipped around and solved for percent complete. | PCIB = EV/BAC | According to the ratio of EV to Budget, you will discover % of work that has been completed by the day selected.